ST MICHAEL’S PRIMARY SCHOOL 1b DIGITAL LEARNING IMPLEMENTO 2020/21

Updated 08/03/2021

ACTION FOR    CHANGE: Digital Learning

Developing the capacity of pupils, teachers and families to use digital technology to support learning and teaching.

Quality Indicators

•	1.3, 2.3, 2.4,3.2

TARGETS

1.	All staff have greater confidence to implement digital learning.

2.	More lessons utilise digital learning resources.

3.	Improved pupil engagement as a result of digital learning experiences.

4.	Use of digital resources to support learning at home increases.

5.	More families have access and capacity to utilise digital learning resources.

Progress Key: Not started  In Progress Complete

| Must Do Tasks | Timescale | Person responsible | Resources inc staff development | Progress |
| --- | --- | --- | --- | --- |
| Timetabling and planning approaches agreed for allocation of resources | August 2020 | A Gallagher DHT DL SIP Group | Time Cleaning process established | Complete |
| Monitor and evaluate the timetabling and planning and adjust accordingly | November 2020 March 2021 | DL SIP Group Class Teachers | Reviewed in light of P7 iPads Review effective distribution of shared iPads in SIP group meetings | Complete |
| 2020/21 Digital Learning SIP group established | Term2 2020/21 | A Stafford HT A Gallagher DHT M O’Neill DHT | Time allocated to this from School QA Calendar Staff development from CAT sessions to inform practice | Complete |
| Staff offered/signposted to CLPL to up-skill in providing Digital Learning experiences | August 2020 ongoing March 2021 | A Gallagher DHT Class Teachers SfLW Staff | During allocated CAT sessions Allocated in-set day Signposted CLPL opportunities GCC webinars • Apple teacher training https://www.apple.com/uk/education/apple-teacher/ • Digital Learning hub: https://sites.google.com/gc.glow.scot/nd-digital-learning-hub/home • iPads Teachable: https://connected-learning-glasgow.teachable.com/ In-house CPD | Ongoing |
| Share implemento with all staff | August 2020 | A Gallagher DHT | Time from In-set Day Glasgow Digital strategy | Complete |
| Share reviewed targets with staff | November 2020 March 2021 | SIP Group | Staff meet time Communication channels (WhatsApp, Email, Paper?) | Complete |
| Remote deployment of Primary and ASL Primary Teacher iPads for new Teachers joining in August – by end October | August – October 2020 | A Gallagher DHT | iPad per staff member | Complete |
| Consultation with teachers | November 2020 March 2021 June 2021 | SIP Group | Communication channels (Glow Forms, WhatsApp, Email, Paper?) | Ongoing |
| Consultation with children | November 2020 March 2021 June 2021 | SIP Group | Children’s Questionnaire devised Communication channels (Glow Forms, letter, text, Twitter, PTA Facebook, diaries) Sharing surveys via Showbie | Ongoing |
| Consultation with parents | November 2020 March 2021 June 2021 | SIP Group | questionnaires Parental skills questionnaire devised Communication channels (Glow Forms, letter, text, Twitter, PTA Facebook, diaries) Sharing surveys via Showbie | Ongoing |
| P7 deployment (deliveries mid-September to early October) | October to end November 2020 | A Gallagher DHT P7 teachers | Pupil individual iPads Letter to parents | Complete |
| Adding new P7 joiners to deployment | Ongoing | A Gallagher DHT P7 teachers | Pupil individual iPad Letter to parents | Complete |
| Apple TV Deployment | October 2020 | A Gallagher DHT Class teachers | Deployment scheduling Apple TV induction | Complete |
| Remaining primary pupils – shared iPad deployment | December to end February 2021 | A Gallagher DHT Class teachers | Pupil shared iPads Timetabling Storage space identified | Complete |
| Every child to be issued up to date Showbie and Glow usernames and passwords | October 2020 | A Gallagher DHT Class teachers | Glow access updated on SEEMIS Assisting with login issues | Complete |
| Best practice in Digital Learning shared | August 2020-May 2021 On-going | A Gallagher DHT DL SIP Group | Bitesize Digital Drop-Ins Visits to other classes/schools Classes covered if required Central forum created to store resources: One Drive/Teams/Other? https://sites.google.com/gc.glow.scot/nd-digital-learning-hub/home Second level innovation group | Ongoing |
| All classes to have issued online tasks as part of blended learning/supporting learning at home. | October 2020 | Class teachers | All staff/pupils have access to online platforms : Showbie/Glow/Teams | Complete |
| Support given for equitable connectivity for pupils at home | June 2020-May 2021 On-going | Teachers SMT | https://connecting.scot Identified by staff/survey Distribution of iPads and Mifi & usage agreements https://www.vodafone.co.uk/mobile/pay-as-you-go-plans/schools-connected | Complete |
| School audit of resources | November 2020 | SIP Group | Assessment of number of classes with/without Apple TV Homes with/without wifi/devices Number of usable legacy iPads (offline) | Complete |
| Digital Learning resources identified and purchased | August 2020-May 2021 On-going | DL SIP Group | Resources acquired through school budget and PEF | Ongoing |
| Approaches to planning reviewed | August 2020 – May 2021 | A Gallagher DHT | Incorporation of new digital learning framework | Complete |
| Digital Learning Family Learning Supports/Events/Videos | August 2020 – May 2021 | A Gallagher DHT | Promoted through family communication channels iPads/Hardware connectivity Support agencies for home learning: VTO Online learning materials http://www.goglasgow.org.uk/Pages/Show/2282 | Ongoing |
| Regular tracking and evaluation meetings | August 2020 – May 2021 Ongoing | SMT | Forward planning meeting calendar | Ongoing |
| Review of a school Digital Learning policies | March 2021 | DL SIP Group | Time allocated to this from School QA Calendar | Complete |
| Impact of DL Strategy measured | March 2021 June 2021 | A Gallagher DHT | Stakeholder (Teacher/Pupil/Family) Questionnaire to be devised | Ongoing |